## Sheet1
Ethical Dilemma on Artic National Wildlife Refuge
Task | Start Date | Days Needed | Completion Date | Adjusted Length
Task 1: Individual Investigation of Possible Project Topics | 2024-09-18 | 2 | 2024-09-20 | 2 | Review Political Landscape | 45552 | 45595
Task 2: Topic Chosen by Team | 2024-09-20 | 2 | 2024-09-24 | 4 | Pros of Drilling in ANWR (Jeremy)
Task 3: Identify stakeholders and issues. | 2024-09-22 | 2 | 2024-09-24 | 2 | Evaluate Economic Benefits
Task 4: Agree upon the stakeholder(s) and issue(s) each team member will investigate further. | 2024-09-23 | 5 | 2024-09-30 | 7 | Assess Energy Independence
Task 5: Begin to make slides. | 2024-09-23 | 20 | 2024-10-21 | 28 | Investigate Technological Advances
Task 6: Further investigation by individual team members, alternative courses of action and the effects from perspective of stakeholder | 2024-10-10 | 10 | 2024-10-24 | 14 | Cons of Drilling in ANWR (Caleb)
Task 7: Correlate perspectives and make a decision. | 2024-10-22 | 2 | 2024-10-24 | 2 | Examine Environmental Impact
Task 8: As a team, use a weighted benefit analysis to show how you made your decision. | 2024-10-18 | 5 | 2024-10-25 | 7 | Research Indigenous Rights
Task 9: Slides compiled for team presentation. | 2024-10-21 | 7 | 2024-10-30 | 9 | Evaluate Climate Change Impacts
Task 10: Presentation during the lab period. | 2024-10-29 | 1 | 2024-10-30 | 1 | Investigate Biodiversity Loss
Conclusion and Ethical Analysis (Max)
Summarize Ethical Dilemmas
Consider Long-term Consequences
Formulas:
Completion Date = WORKDAY([Start Date],[Days Needed])